OPERATOR GUIDE

How to Build a Customer-Specific
12-Month ABX Program

A repeatable walkthrough using the Folloze Academy ABX Blueprint, customer source materials, account intelligence, governed buyer experiences, and measurable revenue outcomes

Designed for: ABM leaders, demand generation, product marketing, RevOps, field marketing, BDR leadership, sales, and Folloze experience owners.

Reusable template | Customer-neutral | Replace placeholders before delivery

# 1. Purpose and final deliverables

This guide explains how to reproduce a rigorous, customer-specific ABX program without copying another customer's strategy, claims, assets, metrics, or assumptions. The method is reusable; the evidence and recommendations must be rebuilt from each customer's own files and systems.

Non-negotiable principle: Use the Academy Blueprint and this operating method as the reusable framework. Treat every customer document, metric, proof point, persona insight, stage threshold, and technology decision as customer-specific evidence that must be revalidated.

## Expected outputs

Executive program summary: segment, objective, campaign thesis, acquisition motions, funnel, value assumptions, and governance.

Completed ABX Blueprint across Alignment, Experiences, Engagement, and Signals.

Twelve-month campaign calendar with personas, content, channels, Folloze experiences, CTAs, opportunity targets, and commercial values.

Persona and buyer-stage journey, content map, dynamic treatment rules, technology/data model, and measurement plan.

Copy-ready prompts for boards, advertisements, email sequences, localization, account research, and optimization.

Crawl-Walk-Run roadmap, launch checklist, ownership model, risks, assumptions, and source log.

## Recommended working artifact

Create one working workbook by copying the Folloze Academy ABX Blueprint. Add execution tabs only after the customer evidence has been collected and the segment and objective are agreed. Keep one companion document for decisions, assumptions, and implementation guidance.

## Definition of done

The target segment is explicit, bounded, owned, and feasible to serve.

Every campaign connects an audience, message, content path, Folloze experience, channel mix, CTA, owner, signal rule, and measurement outcome.

Account progression and opportunity creation replace raw lead volume as the operating metrics.

All customer facts and external claims can be traced to an approved source.

No placeholders, copied customer claims, unsupported benchmarks, or unverified technology assumptions remain in the delivery version.

# 2. Workspace and folder placeholders

Create or identify the folders below before research begins. Replace each placeholder with the customer's actual folder URL or file ID. If a folder does not exist, record that as a content or data gap rather than inventing an input.

| Placeholder | Expected contents | How it is used |
| --- | --- | --- |
| [CUSTOMER_ROOT_FOLDER] | Master workspace for the engagement | All files below |
| [CUSTOMER_STRATEGY_FOLDER] | Corporate strategy, annual plans, growth priorities, market research | Business context and strategic priorities |
| [CUSTOMER_SEGMENT_AND_ACCOUNT_FOLDER] | Segmentation files, account lists, ICP, territory and ownership exports | Target cohort and exclusions |
| [CUSTOMER_INTERNAL_ENABLEMENT_FOLDER] | Discovery decks, sales plays, call recordings, battlecards, FAQs | Pain points, plays, language, objections |
| [CUSTOMER_EXTERNAL_CONTENT_FOLDER] | Public guides, briefs, white papers, reports, webinars | Stage-specific content map |
| [CUSTOMER_STORIES_FOLDER] | Approved customer stories and proof | Industry, use case, outcome, persona proof |
| [CUSTOMER_PRODUCT_TECHNICAL_FOLDER] | Reference architectures, technical briefs, security and integration docs | Technical evaluation paths |
| [CUSTOMER_BRAND_FOLDER] | Brand standards, logos, colors, voice, legal guidance | Board and creative guardrails |
| [CUSTOMER_DATA_EXPORT_FOLDER] | CRM, MAP, intent, web, engagement and campaign exports | Baseline, audience, funnel and measurement |
| [CUSTOMER_EXISTING_CAMPAIGNS_FOLDER] | Current campaigns, nurture, ads, events, boards and performance | Reuse, gaps and performance evidence |
| [CUSTOMER_OUTPUT_FOLDER] | Approved working and final deliverables | Workbook, walkthrough, prompts and source log |

## Required working variables

| Variable | Definition |
| --- | --- |
| [CUSTOMER_NAME] | Customer's approved company name |
| [PROGRAM_SEGMENT] | One bounded segment, not the entire database |
| [TARGET_ACCOUNT_COUNT] | Named-account universe |
| [OPPORTUNITY_TARGET] | Sales-accepted opportunities for the program period |
| [ACQUISITION_MIX] | Net-new, expansion, or a documented split |
| [ACCOUNT_INTELLIGENCE_PLATFORM] | 6sense, Demandbase, another platform, or documented manual substitute |
| [CRM] / [MAP] / [SALES_ENGAGEMENT] | Systems of record and execution |
| [AVERAGE_OPPORTUNITY_VALUE] | Internal planning assumption, with low/base/high values |
| [PROGRAM_START_DATE] | Month 1 anchor |
| [REGIONS] / [LANGUAGES] | Localization scope and ownership |

# 3. Source audit: what to reuse and what to rebuild

The most common failure is treating another customer's completed plan as a template. The reusable unit is the method and table structure—not the final recommendations inside it.

| Reusable methodology | Must be rebuilt for each customer |
| --- | --- |
| Academy pillars: Alignment, Experiences, Engagement, Signals | Segment, account list, exclusions, target volumes and opportunity goal |
| Buyer-stage progression and stage-appropriate content logic | Buying stages, qualification thresholds and conversion assumptions |
| Dynamic 1:many, 1:few, 1:1 and opportunity-room framework | Actual treatment criteria, cohort size, sales capacity and SLAs |
| Technology-role and system-output framework | Installed systems, integrations, data fields and system owners |
| Campaign-calendar and prompt-library structures | Campaign themes, personas, proof, content, channels and creative |
| Crawl-Walk-Run deployment method | Readiness gates, dates, budgets, owners and opportunity pacing |
| Commercial low/base/high scenario method | Average opportunity value, stage probabilities and internal revenue definitions |

## Build a source inventory

Record file name, folder, owner, date, audience, lifecycle stage, claim status, and recommended use.

Separate internal-only materials from externally approved content.

Tag each content item by persona, industry, use case, region, buyer question, stage, and proof type.

Mark unsupported statistics, old brand language, expired links, and conflicting definitions for review.

Maintain a source log so every external claim can be traced during board and ad approval.

## Evidence hierarchy

Customer's current approved strategy, segmentation, CRM definitions, and operating policies.

Customer-authored product, technical, security, and customer-proof materials.

Current performance data from the customer's systems of record.

Approved external analyst, regulatory, partner, and market sources.

Planning assumptions, clearly labeled and assigned an owner/date for validation.

# 4. Intake and decision workshop

Run one structured intake before drafting campaigns. The purpose is to force alignment on what the program is trying to change and what the organization can realistically execute.

## Decision questions

| Decision | Workshop question |
| --- | --- |
| Business objective | What growth problem must this program solve? What counts as a sales-accepted opportunity? |
| Segment | Which one segment can support [TARGET_ACCOUNT_COUNT] named accounts and [OPPORTUNITY_TARGET] opportunities? |
| Acquisition | Is the program net-new, expansion, or a split? How will the motions differ? |
| Feasibility | Can sales, delivery, capacity, partners, and regional teams support the demand created? |
| Buying committee | Which executive, technical, risk, financial, and operational roles participate? |
| Sales plays | Which customer-approved plays or use cases organize the campaign portfolio? |
| Technology | Which system owns account intelligence, experience, nurture, outreach, opportunity, and revenue? |
| Measurement | Which metrics are trusted today? Which require a data audit before use? |

## Required decisions before campaign design

One segment and named-account universe.

Opportunity definition, target, and provisional commercial-value range.

Net-new and expansion treatment rules.

Primary sales plays and approved campaign thesis.

Executive sponsor, program owner, sales owner, RevOps owner, and experience owner.

Systems of record and data-access dependencies.

Stop condition: Do not draft a 12-month calendar when the segment, opportunity definition, ownership, or system of record is unresolved. Document the blocker and complete the decision first.

# 5. Build the program economics

Reverse-engineer the funnel from the opportunity target. Use customer history wherever possible. If history is unavailable, publish assumptions as a range and schedule recalibration after a meaningful sample of opportunities.

## Recommended funnel worksheet

| Funnel stage | Target | Exit criterion |
| --- | --- | --- |
| Named target accounts | [TARGET_ACCOUNT_COUNT] | ICP fit, ownership, acquisition type and suppressions complete |
| Reached accounts | [REACH_TARGET] | Verified paid or owned reach to the intended account/persona |
| Engaged accounts | [ENGAGED_TARGET] | Meaningful experience, content, event, reply, or meeting interaction |
| Buying-group engaged | [BUYING_GROUP_TARGET] | Required number and mix of engaged personas |
| Qualified account | [QUALIFIED_ACCOUNT_TARGET] | Fit plus agreed intelligence and first-party thresholds |
| Qualified meeting | [MEETING_TARGET] | Relevant stakeholder, validated problem, and discovery completed |
| Sales-accepted opportunity | [OPPORTUNITY_TARGET] | CRM opportunity meets the customer's acceptance definition |

## Commercial model

| Scenario | Value | Interpretation |
| --- | --- | --- |
| Low | [LOW_OPPORTUNITY_VALUE] | Conservative gross opportunity value |
| Base | [AVERAGE_OPPORTUNITY_VALUE] | Working planning assumption |
| High | [HIGH_OPPORTUNITY_VALUE] | Upper planning scenario |
| Total gross opportunity value | [OPPORTUNITY_TARGET] × scenario value | Not revenue and not probability-weighted pipeline |

Add monthly opportunity and gross-value targets to the campaign calendar.

Track net-new and expansion values separately even when they share the same total target.

Do not assign revenue or bookings without the customer's probability and timing model.

Recalibrate opportunity value and conversion assumptions after the first [RECALIBRATION_SAMPLE_SIZE] accepted opportunities.

# 6. Complete the Folloze Academy ABX Blueprint

Use the copied Academy workbook as the control structure. Populate each pillar from the customer evidence, not from another account's completed cells.

| Pillar | What to decide | Primary inputs |
| --- | --- | --- |
| Alignment | Define stages, volumes, GTM roles, ABM treatment, goals and opportunity definition. | CRM stages, account intelligence stages, sales process, account segmentation |
| Experiences | Define message approach, personas, content, intent themes and personalization by stage. | Product marketing, content inventory, engagement data, customer research |
| Engagement | Choose when each channel and experience is used across the journey. | Channel capabilities, audiences, permissions, regional plans, seller motion |
| Signals | Translate signal combinations into marketing and sales actions, SLAs, upgrades and downgrades. | Intent, Folloze engagement, CRM context, sales capacity, data governance |

## Stage-design rules

Target/Awareness: educate before asking for a meeting; keep useful content ungated where possible.

Consideration: route by buyer question, persona, use case, region, or workload; use guides and events as soft conversion paths.

Decision: introduce proof, architecture, commercial value, partner validation, and account-specific experiences.

Qualified/opportunity: remove generic nurture friction and use digital sales rooms, stakeholder tracks, FAQs, next steps, and a mutual action plan.

Lost interest: reduce pressure, test a new trigger or proof point, and define re-entry criteria.

## Personalization progression

Start with scalable variables such as persona, region, vertical, use case, and stage. Add account, relationship, technology stack, engaged content, opportunity context, and next milestone only as the account earns deeper treatment.

# 7. Define the technology and data operating model

Do not assume a particular platform. Identify the customer's installed stack, then map each system to one role and one set of required outputs. The experience and handoff should remain coherent even when the vendor names change.

| System | Program role | Required outputs |
| --- | --- | --- |
| [ACCOUNT_INTELLIGENCE_PLATFORM] | Fit, intent, buying stage, audiences, qualification and orchestration | Prioritized accounts, stage movement, intent topics, qualification flags and alerts |
| Folloze | Governed buyer experiences and first-party engagement | Visits, time, assets, CTAs, engaged people, engagement stage and last content |
| [CRM] | Account, opportunity, owner, campaign and revenue source of truth | Acceptance date, value, stage, next step, influence and disposition |
| [MAP] | Known-contact nurture, compliance and suppression | Program status, sends, clicks, opt-outs, membership and board traffic |
| [PAID_MEDIA_PLATFORMS] | Account/persona reach, thought leadership and retargeting | Reach, frequency, engagement, conversions and audience pools |
| [SALES_ENGAGEMENT_PLATFORM] | BDR/AE tasking and human follow-up | Touches, replies, meetings, timing, conversion and disposition |
| [EVENT_PLATFORM] | Peer interaction and technical/executive validation | Target-account attendance, personas, engagement, meetings and follow-up |

## Minimum signal payload for sellers

Account, owner, segment, region, acquisition type, and current stage.

Intent topic and trend, with source and date.

Engaged personas, relationship history, last content consumed, and Folloze engagement stage.

Recommended experience, proof item, CTA, and reason for action.

Known capacity, geography, timing, or delivery constraints.

Facts separated from hypotheses; clear disqualification and downgrade options.

Signal safety: Never trigger senior-level outreach from anonymous intent alone. Require fit plus relevant topic and enough relationship or first-party context to explain why the outreach is useful now.

# 8. Design dynamic treatments and response workflows

Avoid a large permanent Tier 1 list. Start broadly and let verified buying behavior, committee depth, feasibility, and sales validation earn higher-cost treatment.

| Treatment | Volume | Entry/exit logic | Entitlement |
| --- | --- | --- | --- |
| 1:many foundation | All named accounts | Fit, owner, acquisition type and suppressions complete | Paid/owned education, master Folloze experience, light persona routing |
| 1:many → 1:few | Rotating cohorts | Meet [COHORT_THRESHOLD_COUNT] approved conditions across stage, intent, engagement, fit and opportunity status | Cohort board, persona ads, nurture, event and contextual BDR sequence |
| 1:few → 1:1 surge | [ACTIVE_SURGE_ROOM_LIMIT] active accounts | Meet [SURGE_THRESHOLD_COUNT] approved conditions plus AE-validated hypothesis and feasibility check | Account board, matched proof, executive/technical offer and 24-hour response |
| 1:1 → opportunity | Qualified accounts | Validated problem, committee, sponsor, project/timing, next step and sales acceptance | Digital sales room, mutual action plan and opportunity record |
| Downgrade/recycle | Any treatment | No meaningful engagement for [DECAY_WINDOW] and no sales-validated path | Lower paid frequency, re-entry nurture and new trigger test |

## Twenty-four-hour surge workflow

The account meets the approved combined intelligence + Folloze criteria.

The program sends the full seller payload to the owner and BDR/AE team.

The AE validates or rejects the account hypothesis and records the reason.

If validated, the owner sends a contextual board or workshop path within 24 hours.

Marketing upgrades the account experience, suppresses conflicting nurture, and starts committee expansion.

If no path exists, downgrade after the documented decay window and preserve the account experience.

## Acquisition paths

Net-new: Build relationship and committee coverage from problem education through proof and architecture validation. Suppress accounts with active opportunities or protected strategic ownership.

Expansion: Start from verified relationship context. Use champion-forwardable experiences and whitespace hypotheses across business units, regions, workloads, or stakeholder groups. Coordinate with the account team before outreach.

# 9. Build the campaign portfolio and 12-month calendar

Organize campaigns around the customer's approved sales plays or buyer problems. A calendar should balance always-on foundation, focused cohort bursts, proof, events, account surge, opportunity acceleration, and recycle.

## Required campaign record

| Field | Required detail |
| --- | --- |
| Campaign | [CAMPAIGN_NAME] and [SALES_PLAY] |
| Audience | Segment, cohort, account treatment, persona, region and acquisition type |
| Buyer question | The decision or problem the campaign helps resolve |
| Content | Approved customer content and proof by stage |
| Channels | Account intelligence, paid social, MAP, BDR/AE, events, partners, communities, AEO/GEO |
| Experience | Folloze board/room, personalization rules and next-best content |
| Conversion | Stage-appropriate CTA and form/gating rule |
| Signals | Entry, upgrade, seller action, suppression, downgrade and re-entry |
| Economics | Monthly opportunity target and low/base/high gross value |
| Governance | Owner, approvals, source list, launch date and review cadence |

## Calendar design pattern

| Period | Program job | Typical moves |
| --- | --- | --- |
| Months 1–3 | Foundation and learning | Audience/data setup, primary message, master board, early discovery, baseline measurement and first cohorts |
| Months 4–6 | Cohort conversion | Persona/use-case campaigns, technical content, specialist nurture, first events and surge workflow |
| Months 7–9 | Proof and validation | Customer proof, partner ecosystem, workshops, localization and account-specific experiences |
| Months 10–12 | Business case and acceleration | Executive programs, value narratives, digital sales rooms, decision sprint and recycle |

Maintain a cumulative opportunity curve from Month 1 to [OPPORTUNITY_TARGET].

Show monthly low/base/high opportunity value next to the opportunity target.

Keep AEO/GEO and community discovery as supporting layers when relevant; do not let them replace the orchestrated account program.

Use Folloze as the governed destination for campaign traffic; use the customer's website only when it is the best approved content source.

# 10. Create the prompt library

Prompts should be reusable instructions with explicit inputs, constraints, outputs, and quality checks. They should never conceal missing customer facts or invite unsupported claims.

## Board prompt template

Copy-ready prompt: Create a Folloze [BUYER_STAGE] experience for [CUSTOMER_NAME] targeting [PERSONA] in [SEGMENT/REGION]. Buyer question: [BUYER_QUESTION]. Objective: [STAGE_ADVANCEMENT_GOAL]. Use only assets from [APPROVED_CONTENT_FOLDER] and proof from [CUSTOMER_STORIES_FOLDER]. Build: hero, diagnostic or guided path, persona-relevant content, approved proof, and one primary CTA. Personalize by [APPROVED_VARIABLES]. Output the module map, copy, asset placement, CTA labels, personalization rules, tracking requirements, and a claim/source checklist. Do not invent customer facts, outcomes, product capabilities, or statistics.

## Ad prompt template

Copy-ready prompt: Create [NUMBER] [AD_FORMAT] variants for [CUSTOMER_NAME], targeting [PERSONA] at [BUYER_STAGE]. Use one buyer problem per variant and send traffic to [FOLLOZE_URL]. Provide platform-compliant primary text, headline, description, CTA, creative concept, stage rationale, and personalization token. Use only approved claims from [SOURCE_LIST]. Include character counts and a QA table showing persona fit, stage fit, claim source, and CTA alignment.

## BDR sequence prompt template

Copy-ready prompt: Create a five-touch BDR sequence sent on behalf of [AE_NAME]. Inputs: [ACCOUNT], [PERSONA], [BUYING_STAGE], [INTENT_TOPIC], [FOLLOZE_STAGE], [LAST_CONTENT], [RELATIONSHIP_CONTEXT], [BOARD_URL], and [CTA]. Use a personalized opening, approved core message, and contextual close. Touches 1–2 educate; Touch 3 offers a focused review; Touch 4 uses approved proof; Touch 5 respectfully closes. Never say 'I saw you clicked.' Separate facts from hypotheses and include downgrade guidance.

## MAP nurture prompt template

Copy-ready prompt: Create a four-email [MAP] air-cover stream for [PERSONA_GROUP] in [SEGMENT]. Target/Awareness emails are educational and ungated; Consideration uses guides, architecture content, and events; Decision uses proof and a high-value offer. Suppress active opportunity contacts unless sales requests air cover. Output subject lines, body copy, timing, trigger, suppression, Folloze path, CTA, and localization notes.

## Optimization prompt template

Copy-ready prompt: Given [MONTHLY_PERFORMANCE_EXPORT], identify the strongest and weakest combinations by stage, persona, channel, content, board path, CTA, acquisition type, and opportunity outcome. Separate observations from hypotheses. Recommend five prioritized tests with owner, test window, expected impact, success threshold, and rollback condition. Treat small samples as directional.

# 11. Provide executable sequence examples

The final program should include both generation prompts and at least one approved example sequence. Replace the placeholders below using the customer's approved language and content.

| Touch | Timing | Job | Message pattern | CTA |
| --- | --- | --- | --- | --- |
| BDR 1 | Day 1 | Education | [PROBLEM] is creating related questions about [CONSTRAINT]. This short experience summarizes the tradeoffs teams are evaluating. | Explore the resource hub |
| BDR 2 | Day 4 | Diagnostic | Projects often stall when [CONSTRAINTS] must be solved together. Which creates the most drag for your team? | View the decision path |
| BDR 3 | Day 8 | Focused review | A useful next step may be a focused review of [INPUTS], rather than a broad product demo. | 30-minute review |
| BDR 4 | Day 13 | Proof | Here is an approved customer example aligned to [OUTCOME]. The results are theirs, not a guarantee. | Review the proof |
| BDR 5 | Day 18 | Respectful close | If this is not a current priority, I can close the loop and reconnect when the timing changes. | Worth a quick review? |
| MAP 1 | Day 1 | Awareness | Problem education and an ungated Folloze hub. | Explore |
| MAP 2 | Day 10 | Consideration | Persona/use-case path with next-best content. | Choose a path |
| MAP 3 | Day 20 | Specialist | Technical, security, risk, or operational content based on persona and signal. | Review the guide |
| MAP 4 | Day 30 | Decision | Proof and a focused high-value offer; suppress active sales streams. | Request a review |

## Sequence QA

Every touch adds new value; no repeated pitch with a different subject line.

The message reflects a documented persona problem and current stage.

The experience link and CTA match the content of the message.

No surveillance language, invented account facts, unsupported claims, or guaranteed outcomes.

Suppression, exit, downgrade, and re-entry behavior is specified.

# 12. Measurement, governance, and optimization

Measurement should answer whether the right accounts and buying groups are progressing toward accepted opportunities and commercial value. Activity metrics are diagnostic, not the program objective.

| Area | Business question | Measures | Cadence / owner |
| --- | --- | --- | --- |
| Target | Are the intended accounts and personas reachable? | Coverage, match rate, contact depth, reach and frequency | Weekly / Marketing Ops |
| Awareness | Are accounts recognizing the problem? | Engaged accounts, people, dwell, completions and return visits | Weekly / Campaign Lead |
| Consideration | Are buying groups exploring a path? | High-value assets, repeat visits, persona depth, events and replies | Weekly / ABM + BDR |
| Decision | Are accounts validating proof and architecture? | Proof engagement, workshops, surge-room depth and high-value CTAs | Daily alerts; weekly account review |
| Opportunity | Are accepted opportunities and value being created? | SAOs, low/base/high gross value, progression, next-step age and committee depth | Weekly pipeline; monthly executive review |
| Content | Does content advance accounts? | Next-step CTR and stage progression after content—not downloads alone | Monthly / Content |
| Experience | Are Folloze paths useful and personalized? | Visits, time, assets, CTAs, people and engagement-stage progression | Weekly / Experience Lead |
| Sales execution | Are signals receiving useful action? | SLA, acceptance, disposition, meeting quality and negative feedback | Daily / Sales Ops |
| Commercial | Is the program on pace economically? | Actual vs target SAOs and low/base/high value by month and acquisition type | Monthly / RevOps |
| Governance | Can teams trust and reuse the program? | Template adoption, source completeness, tracking, data quality and compliance | Monthly COE council |

## Optimization rules

Optimize one major variable at a time: audience, message, content order, CTA, channel, or seller action.

Prioritize account progression and opportunity outcomes over isolated CTR improvements.

Require sufficient sample size or label the result directional.

Review upgrade/downgrade criteria quarterly and after meaningful conversion changes.

Document every major assumption, owner, validation date, and replacement value.

# 13. Crawl-Walk-Run implementation roadmap

| Phase | Timing | Objective | Exit gate |
| --- | --- | --- | --- |
| Crawl | Months 0–3 | Create the data, audience, experience, sequence and dashboard foundation. | First [CRAWL_SAO_TARGET] SAOs; end-to-end signal test passes |
| Walk | Months 3–6 | Launch rotating cohorts, persona paths, events, contextual BDR action and first surge rooms. | [WALK_ADDITIONAL_SAOS] additional SAOs; repeatable cohort conversion |
| Run | Months 6–12 | Scale globally, localize within guardrails, operate surge rooms and support all SAOs with digital sales rooms. | [RUN_ADDITIONAL_SAOS] additional SAOs; [OPPORTUNITY_TARGET] total |

## First 30 days

Confirm target account list, acquisition type, ownership, regions, verticals, personas, suppressions, and feasibility fields.

Complete source inventory, content tagging, CRM/data audit, and technology-role mapping.

Define stages, qualification, opportunity acceptance, funnel math, commercial assumptions, and monthly pacing.

Approve program thesis, sales plays, master Folloze experience, first audience, and measurement baseline.

## Days 31–60

Launch the 1:many foundation and first persona/region/use-case cohorts.

Activate MAP, paid media, BDR enablement, event plan, AEO/GEO support, and dashboard.

Build proof taxonomy, specialist paths, net-new sequence, and champion-forwardable expansion experience.

Test the combined signal payload and twenty-four-hour surge workflow.

## Days 61–90

Upgrade the first qualified accounts into 1:1 surge rooms.

Run the first architecture, executive, peer, or specialist event motion.

Measure account progression, seller action, commercial pace, content performance, and data quality.

Adjust cohort selection, rules, content, sequence, and value assumptions before scaling.

# 14. Final delivery and QA checklist

☐ All folder placeholders have been replaced or intentionally marked as missing inputs.

☐ The copied Academy Blueprint is completed with customer-specific evidence.

☐ The segment, account count, acquisition mix, opportunity goal and value assumptions are explicit.

☐ Net-new and expansion motions are distinguishable in audience, messaging, routing and reporting.

☐ The technology model reflects the customer's installed systems and owners.

☐ Every campaign has an audience, message, content path, Folloze destination, CTA, signal rule and owner.

☐ Upgrade, downgrade, suppression, recycle and twenty-four-hour surge rules are documented.

☐ The calendar includes monthly opportunity pacing and low/base/high value.

☐ At least one BDR sequence and one MAP nurture are fully written, tested and approved.

☐ AEO/GEO, community, events, partner and field activities are integrated only where they support the account program.

☐ Capacity, geography, density, timing and delivery feasibility are checked before opportunity acceptance.

☐ Claims, proof and external statistics are traceable to approved sources.

☐ Intent-only outreach and surveillance language are prohibited.

☐ The dashboard shows account progression, buying-group depth, SAOs, value, SLAs and data quality.

☐ Executive sponsor, program owner, regional owners and platform owners have accepted the operating cadence.

## Handoff package

[FINAL_ABX_WORKBOOK_URL]

[FINAL_WALKTHROUGH_DOCUMENT_URL]

[APPROVED_SOURCE_LOG_URL]

[BOARD_AND_PROMPT_LIBRARY_URL]

[DASHBOARD_URL]

[LAUNCH_CHECKLIST_AND_RACI_URL]

Final caution: Before sharing externally, remove internal-only notes, validate every claim and planning value, confirm permissions on all linked folders, and run a final test of every experience, CTA, form, alert, suppression, and seller handoff.